# SME Chapter Event Planning 3-Month Timeline

## 3 Months Before the Event

- Define event goals and objectives

- Set the event date and reserve the venue

- Establish a planning team and assign roles

- Create a preliminary budget

- Develop sponsorship packet and begin outreach

- Identify and invite potential speakers or special guests

- Research and apply for necessary permits or insurance

- Draft a high-level event agenda

2 Months Before the Event

- Launch promotional campaign (social media, email, website)

- Confirm all venue logistics (seating, A/V, parking, accessibility)

- Finalize sponsors and confirm benefits/recognition

- Secure speakers and collect bios/headshots

- Order supplies (badges, signage, tablecloths, giveaways)

- Open registration or ticketing

- Begin recruiting volunteers or staff

1 Month Before the Event

- Send confirmation emails to speakers and sponsors

- Conduct a walk-through of the venue

- Finalize run-of-show and staffing assignments

- Test A/V needs and order rentals

- Prepare materials: programs, name tags, banners

- Promote through chapter newsletters, partners, and SME channels

- Confirm catering (if applicable)

1–2 Weeks Before the Event

- Send reminders to attendees and speakers

- Confirm volunteer shifts and responsibilities

- Assemble event kits (welcome packets, signage, swag)

- Double-check logistics: Wi-Fi, parking, room setup

- Hold a team briefing to walk through the schedule

- Prepare talking points and announcements

Event Day

- Arrive early for setup and coordination

- Check in guests and provide materials

- Manage timekeeping and transitions

- Monitor A/V and venue logistics

- Thank speakers and sponsors during the event

- Collect feedback or surveys if applicable

- Take photos or video for post-event sharing

1 Week After the Event

- Send thank-you emails to speakers, sponsors, and attendees

- Share highlights and photos on social media

- Conduct a post-event debrief with the planning team

- Document lessons learned and improvement areas

- Reconcile budget and submit final report

- Archive materials for future events